## User_Stories
Planned Sprint | US ID | User Story Description | MOSCOW | Assignee | Status
Sprint 1 | US001 | As a developer, I want to upload Python code so the system can parse it for syntax errors. | Must Have | Developer | Completed
Sprint 1 | US002 | As a developer, I want to see unused variables and imports so I can clean my code. | Must Have | Developer | Completed
Sprint 2 | US003 | As a user, I want AI-driven suggestions (Gemini) for code improvement and PEP8 compliance. | Must Have | Developer | Completed
Sprint 2 | US004 | As a user, I want a "Get New Suggestion" button to receive varied AI feedback. | Should Have | Developer | Completed
Sprint 3 | US005 | As a multi-language developer, I want to submit non-Python code for AI review. | Could Have | Developer | In Progress

## Tasks
US ID | Task ID | Task Description | Team Member | Activity | Original Estimate (Hrs)
US003 | T001 | Integrate Google Gemini Pro API via ai_suggestor.py. | Developer | Development | 6
US003 | T002 | Create .env and st.secrets logic for secure API key management. | Developer | Security | 2
US004 | T003 | Implement st.session_state in app.py to track suggestion history. | Developer | UI/UX | 4
US004 | T004 | Update AI prompt to request DIFFERENT suggestions based on history. | Developer | Prompt Eng. | 2