## Sheet1
Sl No | Description | Detected Sprint | Type Of Defect | Status | Remarks
1 | App crashes when code_input is empty. | Sprint 1 | Logical | Closed | Added .strip() validation.
2 | Gemini API key exposed in public GitHub repo. | Sprint 2 | Security | Closed | Moved key to .env and added to .gitignore.
3 | code_parser fails on non-Python code. | Sprint 3 | Standards | Open | Need to bypass parser for non-Python languages.